P33 - A Self-Hosted Open-Source Radiology Information System (RIS)

| Group Formal Tag: | COMP3888_W10_03 |
| --- | --- |
| Tutor Name: | Zilin Zhang |
| Client Name: | Louis Gan |

Group members details

(indicate if any member is doing multiple units)

| No. | Student Name | Student ID | Student Unikey | XP-Roles |
| --- | --- | --- | --- | --- |
| 1 | Mavis Xie | 540729001 | yxie0455 | Front-end Programmer |
| 2 | Zhongyang Sun | 541043667 | zsun0958 | Back-end Programmer |
| 3 | Maggie Wang | 540030181 | xwan0180 | Tester |
| 4 | Cheryl Huynh | 530609142 | phuy0123 | Researcher |
| 5 | Dulguun Erdenebayar | 530829588 | derd0098 | Tracker |
| 6 | Vincent Yau | 540496066 | vyau0339 | GitHub Expert |
| 7 | Tarek Fahmi | 530135191 | tfah7333 | Manager |
| 8 | Jackson Mei | 540234918 | jmei0161 | Report writer |

Attendances: everyone in the group

Apologies: none absent

Submission Date: 16/08/2026

Weekly Group Meeting Minutes

Time: 12 Aug 2026, the 1st group meeting

Venue: H70.01.1070.Belinda Hutchinson Building

Meeting Minute Taker: Cheryl Huynh, Jackson Mei

| # | Agenda Item | Description/ Comments | Decision/Action | Who? | Items for escalation |
| --- | --- | --- | --- | --- | --- |
| 1 | What has been completed? | Discussed the project requirements and overall RIS workflow. Initial team roles and responsibilities for the first few weeks were assigned. | Agreed on the initial task allocation and project understanding. | Everyone | N/A |
| 2 | What is in progress? | Preparing questions for the first client meeting. Team members are cloning the repository, exploring the project structure, setting up the local development environment, and learning the required technologies, including Angular + TypeScript, Spring Boot + PostgreSQL, Docker, and the GitHub workflow. | Continue learning the project technologies and complete the environment setup before development begins. | Everyone | N/A |
| 3 | What is working well? | Team communication was effective, and everyone actively contributed to the discussion. Initial project planning and task allocation were completed smoothly. | Maintain regular communication and collaborative discussions. | Everyone | N/A |
| 4 | What needs improvement? | The team needs to become more familiar with the project structure, development workflow, and required technologies. Further understanding of each member's responsibilities and better coordination of tasks are also needed as the project progresses. | Continue self-learning and knowledge sharing within the team, and complete the required development environment setup before implementation begins. | Everyone | N/A |
| 5 | Reminders | Clone the project repository, understand the project structure, run the project locally, install and configure the required development tools. | Ensure everyone has a working local development environment before implementation starts. | Everyone | N/A |
| 6 | What needs to be completed before the next meeting? | - Finalise the list of questions for the first client meeting. - Clone the repository and understand the project structure. - Run the project locally. - Learn the project technologies, including Angular + TypeScript (frontend) and Spring Boot + PostgreSQL (backend). | Complete the preparation tasks before the client meeting and be ready to start development. | Everyone | N/A |
| 7 | What’s Next | Attend the first client meeting to clarify project requirements, confirm the development workflow and technical details, then begin system design and implementation planning. | Continue project planning based on client feedback and begin development tasks. | Everyone | N/A |
| … | ….. |  |  |  |  |

Main Discussions

- Project Understanding and Workflow
 Team members shared their initial understanding of the project. The overall project workflow, system structure, required technologies, GitHub repository setup, development workflow, and important considerations were introduced and discussed to ensure that all members had a common understanding of the project.

- Team Contract and Working Agreements

The team discussed and agreed on the team contract, including expectations for communication, attendance, task completion, collaboration, and individual responsibilities. Key working principles and important considerations were agreed upon to ensure effective teamwork and accountability throughout the project.

- Team Roles and Task Allocation
 The team discussed and assigned preliminary roles and responsibilities for Weeks 2–5. A rotating role arrangement was adopted so that members can take on different responsibilities each week, such as programming, project management, report writing, and other project-related tasks. This allows all members to gain experience in different aspects of the project.

- Technical Stack and Development Requirements
 The team reviewed the main technologies and tools required for the project, including Angular and TypeScript for frontend development, Spring Boot and PostgreSQL for backend development and data management, Docker for containerization and deployment, and GitHub for collaboration. The team also discussed the basic responsibilities of the frontend and backend components.

- Preparation for the Client Meeting
 The team identified several project requirements and technical details that require further clarification from the client. Questions were prepared for the upcoming client meeting to confirm the project's scope, expected functionality, technical requirements, and other uncertainties before further development.

- Task Management and Project Progress
 Following the initial task allocation, the project manager further divided the work into specific tasks in Jira. Each member's responsibilities, expected deliverables, and current task status were recorded so that everyone could clearly understand what needed to be completed during the week.

Key Takeaways

- Angular + TypeScript will be used for frontend development, providing user interfaces for patient registration, scheduling, worklists, and reporting.

- Spring Boot + PostgreSQL will support the backend and database, handling REST APIs, business logic, patient/exam data, and workflow status management.

- Docker and Docker Compose will be used to containerize and deploy the complete system, providing a consistent development and deployment environment.

- GitHub will be used for version control and collaborative development, including branches, pull requests, code reviews, and integration of team members' work.

- Jira will support task allocation and progress tracking, allowing each member to clearly identify their responsibilities and expected deliverables.

- A rotating role arrangement for Weeks 2–5 was established, and key questions were prepared for further clarification with the client.

What Happened

- Established a shared understanding of the project scope and workflow.

- Agreed on the team contract and working principles.

- Allocated rotating roles and responsibilities for Weeks 2–5.

- Identified the main development technologies and tools.

- Assigned individual tasks and deliverables through Jira.

- Prepared key questions for the upcoming client meeting.

What’s Next

- [All Team Members] Keep up to date with changes on GitHub, become familiar with the required development tools and software, and review the project structure and workflow to prepare for upcoming development tasks.

- [Maggie] Draft the Project Abstract/Summary and Background sections of the Project Scope & Proposal Report, delivering a clear overview of the proposed RIS, its purpose, context, and key project background.

- [Dulguun] Draft the Project Introduction and context section of the Project Scope & Proposal Report and coordinate team task allocation to ensure each member has clearly assigned responsibilities and deliverables.

- [Cheryl] Draft the Project Aims & Objectives section of the Project Scope & Proposal Report and assist with team task allocation, delivering a clear set of project aims and objectives and well-coordinated task assignments among team members.

- [Zhongyang] Draft the Proposed Technical Architecture & Computational Solutions section of the Project Scope & Proposal Report and prepare the required project resources, delivering a clear technical architecture proposal and the necessary supporting resources for the team.

- [Jackson] Draft the Software & Hardware Resources and Roles & Responsibilities of Group Members sections of the Project Scope & Proposal Report, and complete the Week 2 meeting minutes, delivering a clear summary of the resources, and key meeting outcomes.

- [Tarek] Draft the Proposed Computational Solutions: Testing & Analysis and Deployment sections of the Project Scope & Proposal Report, delivering a clear testing and analysis strategy and a practical deployment approach for the proposed system.

- [Mavis] Draft the Expected Outcomes and Milestones / Schedules sections of the Project Scope & Proposal Report and record the client meeting, delivering clearly expected project outcomes, and timeline, and a complete record of the client’s feedback and requirements.

- [Vincent] Draft the High-Level Technical Architecture, Feasibility Analysis, and Risk Mitigation sections of the Project Scope & Proposal Report, delivering a clear system architecture, feasibility assessment, and strategies for managing potential project risks.

Weekly Client Meeting Minutes

Time: 13 Aug 2026, the 1st client meeting

Venue: https://uni-sydney.zoom.us/j/86204586994

Meeting Minute Taker: Mavis

Attendances: Mavis, Cheryl, Dulguun, Maggie, Vincent, Tarek, Jackson

Apologies: Zhongyang

| # | Agenda Item | Description/ Comments | Decision/Action | Who? | Items for escalation |
| --- | --- | --- | --- | --- | --- |
| 1 | What has been completed? | Introductions completed and regular client meeting time discussed. | Weekly client meeting set for Tuesdays at 7 pm, online. | All attendees | Relay meeting time to absent member. |
| 2 | What is in progress? | Clarifying RIS workflow, user roles, DICOM requirements and project scope. | Draft a role/permission matrix and investigate DICOM/DCMTK. | Group | Clarify evaluation/SCU configuration if required. |
| 3 | What is working well? | Initial project requirements and expected workflow were clarified with the client. | Continue weekly progress discussions with client. | Group | N/A |
| 4 | What needs improvement? | Further understanding of DICOM Modality Worklist and DCMTK is required. | Research and test the relevant DICOM tools/requirements. | Group | Raise technical uncertainties with client/tutor. |
| 5 | Reminders | Future meetings should include a short recap of the previous meeting and progress made. | Prepare simple progress slides for each weekly client meeting. | Group | N/A |
| 6 | What needs to be completed before the next meeting? | Role permissions and initial technical approach need further development. | Draft permission matrix; investigate DCMTK/DICOM; begin defining implementation approach. | Group | Confirm any unresolved technical/evaluation requirements. |
| 7 | What’s Next | Begin development based on agreed requirements and continue refining project scope. | Start implementation and present progress at the next client meeting. | Group | N/A |
| … | ….. |  |  |  |  |

Main Discussions

- Asked client about the project split into two parts – booking system & medical --> want to know who is the next patient, radiologist push search machine and system asks RIS (radiology system) and returns a list of patients they must scan today. No manual input.

  - Machine rules: 4 rows – receptionist, schedule, tech, admin

  - Order, schedule, acquire & complete

- Which user roles must the system support?

  - There should be at least 4 roles – draft permission matrix to present next meeting

- Send results to scanner - do we need to confirm?

  - Must acquire and then report before completing

- Matching requirements?

  - Can be decided by group

- Any examples to follow?

  - Client suggestion – in final evaluation will be decided by DCMTK, try the DCMTK, download patient data from internet to test program

- Will you provide a specific SCU for the DKM configuration?

  - Must confirm with tutor, do not receive mark sheet until week 6

- For future meetings – online preferred

- Progress updates:

  - Make simple slides for following weekly meetings that shows what we have discussed last week

  - Show progress from last week

- Patient cancel:

  - Only allowed before acquired, if you want to reschedule the status is kept

- UI requirements for the page itself:

  - Do not need to worry about it, no requirement for fancy UI

  - Main point is DACOM

Key Takeaways

- At least four user roles are required; permission matrix to be drafted.

- DICOM integration is the main technical priority.

- Exam lifecycle and cancellation/rescheduling rules need to be enforced.

- DCMTK should be investigated for DICOM testing.

- UI can remain simple.

- Weekly client meetings: Tuesdays at 7:00 pm via Zoom.

What Happened

- Client introduction.

- Clarified the expected RIS workflow and major technical requirements.

- Discussed user roles, exam statuses, cancellation/rescheduling and DICOM testing.

- Established the format and regular time for future client meetings.

What’s Next

| Member | Week 2 role | Task before next client meeting |
| --- | --- | --- |
| Dina | Tracker | Track everyone's Week 2 tasks/progress and update Jira/project tracking. |
| Tarek | Manager | Coordinate the role/permission matrix and consolidate the group's decisions. |
| Zhongyang | Backend | Investigate DICOM MWL/DCMTK implementation from the backend perspective. |
| Maggie | Tester | Investigate how DCMTK/findscu can be used to test C-FIND matching and what test cases will be needed. |
| Cheryl | Researcher | Research DICOM matching behaviour/keys and summarise findings for the group. |
| Jackson | Report Writer | Prepare the next client-meeting progress slides, including this week's decisions and progress. |
| Mavis | Frontend | Begin the frontend structure/UI for the agreed RIS workflow, using the client clarification that the UI can remain simple. |
| Vincent | GitHub Expert | Investigate/clarify the SCU/DCMTK configuration and ensure the repo/development workflow is ready for implementation. |

Individual Progress Report

Name:  Mavis Xie

Student ID: 540729001

Goals

As the frontend programmer this week, I:

- Became familiar with the Angular + TypeScript frontend and existing project structure.

- Set up the project locally and prepare for frontend development.

- Attended the first client meeting and clarify requirements relevant to the frontend and overall RIS workflow.

- Recorded the client meeting requirements and decisions.

Progress Made

- Reviewed the project structure and began familiarizing myself with the frontend technology and development workflow.

- Attended the first client meeting and recorded the key requirements and decisions.

- Clarified requirements relevant to future frontend development, including the expected RIS workflow, user roles, exam status lifecycle and cancellation/rescheduling behavior.

- Confirmed with the client that the UI can remain simple, with DICOM integration and workflow functionality being the main priority.

- Frontend implementation has not yet substantially begun, as this week primarily focused on project setup and requirements clarification.

Blockers to Progress/Issues

- I had to wait for client clarification with UI requirements, which blcoked progress with front end development.

- As this was the initial setup and requirements-gathering week, there was limited frontend implementation completed.

Individual Progress Report

Name: Dulguun Erdenebayar

Student ID: 530829588

Goals

As a weekly Project Tracker, my goal was to monitor each team member's progress across Git, Jira, and weekly reports. As General Manager, my main focus was building a positive team atmosphere and improving communication across the group. Specific goals for the week included publishing and assigning all Jira tasks through Week 4, clarifying reporting and contract expectations with our tutor, and resolving key technical questions with the client — including acquisition overflow handling, UI design direction, matching rules, and project scope.

Progress Made

- Tracked each team member's progress through Git activity, the Jira board, and individual weekly reports.

- Fostered a positive team atmosphere and worked to improve communication across the group.

- Created and assigned all Jira tasks through Week 4.

- Began drafting the Project Scope and Proposal document, focusing on the Introduction/Context and Aims sections, alongside the Week 4 presentation slides.

- Clarified key technical questions with the client, including acquisition overflow, UI design, matching rules, and project scope.

- Clarified reporting and contract expectations with the tutor.

- Finalised Git and Docker setup on my personal development machine.

Progress aligned with this week's goals, with the addition of early work on the proposal document and presentation slides, which was started ahead of schedule.

Blockers to Progress/Issues

- Jira planning beyond Week 4 was difficult, since the project was still in an early research phase — task breakdown across frontend and backend couldn't be finalised until all members completed their initial research, and the workstreams were divided. This will resolve naturally as the team moves past the research phase.

- Coordinating weekly meetings was difficult due to members' conflicting schedules, though we managed to find 2–3 workable time slots. No group or client decision is needed here yet, but it's worth flagging if it continues to constrain meeting frequency.

Individual Progress Report

Name: Vincent Yau

Student ID: 540496066

Goals

As the GitHub expert for week 2, my goals were to:

- Support team members with repository access and Git related setup issues

- Become familiar with the project repository structure and development workflow

- Assist with preparing repository and development workflow for implementation

- Clarify SCU/DCMTK configuration required for testing DICOM modality worklist.

- Attend the client meeting and clarify technical requirements relating to DICOM, DCMTK and the overall RIS workflow.

Progress Made

- Everyone was able to access the repository and clone the repository on their personal device

- Remained available to help with GitHub related issues and became more familiar with the repository structure and expected development workflow.

- Attended the first client meeting and clarified several important DICOM requirements as a group. (recorded in meeting notes)

- Become more familiar with the overall project architecture, including how the frontend, backend, database and DICOM components will interact.

- Set up Git and docker on personal system

Blockers to Progress/Issues

- The exact DCMTK version and SCU configuration required for final testing have yet to be confirmed and will need to be clarified with the tutor or coordinator in later weeks.

- As the project is still in the initial setup and research stage, the final DICOM testing and integration workflow has not been established yet.

- No significant GitHub related blockers were encountered this week, as all team members were able to access and clone the repository successfully.

Individual Progress Report

Name: Maggie Wang

Student ID:540030181

Goals

- Review the client meeting questions and help prepare the team for the first client meeting.

- Attend the client meeting and record the client’s key requirements and decisions.

- Clarify the expected project scope, user roles, examination workflow, DICOM Modality Worklist requirements and testing approach.

- Review the Project Scope and Proposal document against the requirements confirmed by the client.

- Organize and upload the meeting key points to the team’s shared Meeting Minutes folder.

Progress Made

- Attended the client meeting and recorded the main requirements.

- Documented the four main staff roles: receptionist/scheduler, technologist, radiologist and administrator.

- Recorded the required examination workflow: Ordered → Scheduled → Acquired → Reported → Completed

- Documented that C-FIND and Modality Worklist retrieval are read-only operations.

- Recorded that acquisition may be simulated using a “Mark as Acquired” action.

- Confirmed that examinations can only be cancelled before acquisition and that invalid status transitions must be rejected.

- Organized and uploaded the meeting key points to the team’s shared Meeting Minutes folder.

Blockers to Progress/Issues

- The detailed permissions for each user role still need to be confirmed by the team.

- The DCMTK version and final testing configuration have not yet been confirmed.

- The project scope and requirements still require formal client approval.

Individual Progress Report

Name: Jackson Mei

Student ID:540234918

Goals

- Complete the Software and/or Hardware Resources and Roles & Responsibilities of Group Members sections of the Project Scope & Proposal Report.

- Prepare and summarize the Week 2 meeting minutes.

- Keep up to date with the GitHub repository and improve my understanding of the project structure, workflow, and required development tools.

- Learn the basics of Angular and TypeScript for frontend development, become familiar with the required development tools.

Progress Made

- Drafted the assigned sections of the Project Scope & Proposal Report by identifying the key software/hardware resources required for the project and summarizing the roles and responsibilities of group members.

- Completed the Week 2 meeting minutes, including the main discussions, key takeaways, completed activities, and upcoming tasks.

- Attended the client meeting and recorded key discussion points and requirements for future reference.

- Cloned the latest GitHub repository to my local environment and reviewed the file structure to gain a better understanding of the project architecture.

- started familiarizing myself with the required development tools and frontend technologies, including Angular, Docker.

Blockers to Progress/Issues

- Some project requirements and technical details still require clarification, which may affect the final definition of team responsibilities and development tasks.

- The project scope and requirements are still awaiting formal client confirmation

- Some development tools are still new to the team, requiring further communication, coordination, and knowledge sharing among members to build a common understanding and use them effectively.

Individual Progress Report

Name: Zhongyang Sun

Student ID: 541043667

Goals:

- Decide the project architecture and technology stack.

- Set up a containerised development environment.

- Establish the initial frontend, backend, and database structure.

- Define a consistent Git and development workflow for the team.

Progress Made

- I selected and documented the modular-monolith architecture and technology stack.

- I set up the Angular 21 frontend, Spring Boot 4 backend, and PostgreSQL 17 database.

- I created the Dockerfiles and Docker Compose configuration for running the complete application.

- I documented the local setup process, architecture boundaries, and team development workflow.

- The initial architecture and environment setup goals were satisfied.

Blockers to Progress/Issues

- Client confirmation is required on whether exam acquisition should be recorded manually in the RIS or through a separate DICOM/HL7 message.

- The group needs to decide which exam states allow cancellation.

- Role permissions, detailed domain models, and DICOM field mappings still need group discussion.

- Other team members need to test and confirm that the Docker setup works correctly on their machines.

Individual Progress Report

Name: Cheryl Huynh

Student ID: 530609142

Goals

- Dividing the project into phases

- Setting up Jira to track project tasks

- Diving week 3 project scope and proposal for team members

- Organizing team members roles

- Setting meetings with client

- Looking into projects scope and architecture

- Setting up project in my local computer and getting it working (Git and Docker)

- Understanding our team project scope and initial project backbone

- Attend client meeting and group meeting

Progress Made

All goals satisfied

Blockers to Progress/Issues

- Understand team members strengths to allocate suitable tasks

- Finding a suitable time for weekly meetings

Individual Progress Report

Name: Tarek Fahmi

Student ID: 530135191     UniKey: tfah7333

Goals

Coordinate Week 2 planning, role allocation, action ownership and accurate communication of team decisions.

Turn the first client meeting's requirements into a permission matrix and proposed testing/deployment deliverables.

Progress Made / Major Achievements

I attended the in-tutorial group meeting and first client meeting, contributing to role allocation, task planning, client questions and clarification of the order-to-completion RIS workflow.

I signed the group contract and accepted my Week 2 role, including responsibility for promptly maintaining team information; the contract and meeting minutes provide my tutorial evidence.

I assumed ownership of coordinating the four-role permission matrix, consolidating decisions, and drafting the proposed Testing & Analysis and Deployment sections.

Blockers to Progress / Major Issues

The detailed permission matrix and proposed scope still require client review and sign-off.

The DCMTK version, SCU configuration and assessment-evidence requirements await tutor or coordinator confirmation.

A final testing or deployment plan cannot be claimed until the technology stack, workflow rules and demonstration environment are confirmed.

Plan for Next Week

Produce a four-role permission matrix covering create, view, edit, schedule, reschedule, cancel, acquire, report, complete and administrative actions for client review.

Draft proposed Testing & Analysis content covering lifecycle, permissions, C-FIND matching and synthetic-data tests, plus a reproducible self-hosted Deployment approach.

Label unresolved choices Proposed/TBC, update the tracker with owners and approval status, and raise DCMTK/SCU evaluation questions with the tutor or coordinator.